pwc ¦ MUY Monthly Progress Report Mukhyamantri Udyamshala Yojana August 2026 Private & Confidential

# Contents

| 1. | Progress in Mukhyamantri Udyamshala Yojana (MUY) ................................................................ |
| --- | --- |
| 2. | Quantitative Progress - Plan vs Achievements ................................................................ |
| 3. | District-wise Progress ................................................................ |
| 4. | Program Workstream Progress ................................................................ |
| 5. | Field Highlights ................................................................ |
| 6. | Report Basis and Data Notes ................................................................ |

# 1. Progress in Mukhyamantri Udyamshala Yojana (MUY)

This Monthly Progress Report presents MIS-recorded progress for August 2026. Targets and achievements follow the approved MUY deliverables matrix for FY 2026-27.

| 909 CFA applications | 0 Incubatees onboarded | 26 Indicators reporting progress |
| --- | --- | --- |

## Key monthly highlights

- Call for Application: 909 achieved against a monthly target of 1,470.

- Participants in Awareness cum Outreach activities: 574 achieved against a monthly target of 910.

- Incubatees taken Part in Business Modules Training: 212 achieved against a monthly target of 700.

- Business Model Canvas: 185 achieved against a monthly target of 600.

- Business Registration: 74 achieved against a monthly target of 600.

- Schematic Convergence: 48 achieved against a monthly target of 300.

- Specialized Mentorship Support: 25 achieved against a monthly target of 65.

- No. of Awareness cum Outreach activities for SHG members/Potential Lakhpati Didis/ SHGs/CBOs etc.: 24 achieved against a monthly target of 122.

# 2. Quantitative Progress - Plan vs Achievements

The table below presents the approved monthly target and MIS-recorded achievement for August 2026.

| S.No. | Indicator | Type of Indicator | Target | Achievement | Achievement (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Outreach and Mobilisation |  |  |  |  |
| 1.1 | Call for Application | Key Indicator | 1,470 | 909 | 62% |
| 1.2 | District Level Workshops | Key Indicator | — | 3 | — |
| 1.3 | No. of Awareness cum Outreach activities for SHG members/Potential Lakhpati Didis/ SHGs/CBOs etc. | Non-Key | 122 | 24 | 20% |
| 1.3.1 | Participants in Awareness cum Outreach activities | Non-Key | 910 | 574 | 63% |
| 1.4 | EAP/EDP Sessions | Key Indicator | 13 | 12 | 92% |
| 1.5 | Outreach through Community Organizations | Non-Key | 4 | 0 | 0% |
| 2 | Identification and Onboarding of Enterprises |  |  |  |  |
| 2.1 | Incubatees Onboarded | Key Indicator | 700 | 0 | 0% |
| 2.1.1 | Onboarding of Potential Lakhpati Didi/ SHG Members/ CBOs* | Key Indicator | 300 | 0 | 0% |
| 3 | Training & Capacity Building |  |  |  |  |
| 3.1 | Business Skills Training Sessions | Key Indicator | 39 | 7 | 18% |
| 3.2 | Incubatees taken Part in Business Modules Training | Non-Key | 700 | 212 | 30% |
| 3.3 | Technical Trainings to Incubatees | Non-Key | 1 | 0 | 0% |
| 3.3.1 | Technical Trainings to Potential Lakhpati Didis/ SHG Members/ CBOs | Non-Key | (Need Based) | 1 | — |
| 3.4 | Capacity Building of stakeholders (REAP, USRLM, Other Line department staff) | Key Indicator | 0 | 0 | — |
| 4 | Business Formalization |  |  |  |  |
| 4.1 | Business Registration |  |  |  |  |
| 4.1.1 | Business Registration | Key Indicator | 600 | 74 | 12% |
| 4.2 | Legal & Licensing Support |  |  |  |  |
| 4.2.1 | Artisan Card | Key Indicator | 26 | 8 | 31% |
| 4.2.2 | FSSAI | Non-Key | 75 | 14 | 19% |
| 4.2.3 | UTDB | Non-Key | 20 | 1 | 5% |
| 4.2.4 | GST Registration | Non-Key | 35 | 4 | 11% |
| 4.2.5 | Trademark application filling | Non-Key | 0 | 1 | — |
| 4.2.6 | GI Seller Registration | Non-Key | — | 0 | — |
| 4.2.7 | Advance Licensing Support (Mandi Licensing, Lab Test etc.) | Non-Key | (Need Based) | 1 | — |
| 5 | Mentorship |  |  |  |  |
| 5.1 | Specialized Mentorship Support | Key Indicator | 65 | 25 | 38% |
| 5.2 | Mentorship Support through online portal | Non-Key | 0 | 0 | — |
| 6 | Partnership & Forward Linkages |  |  |  |  |
| 6.1 | No of Partners outreach | Non-Key | 10 | 11 | 110% |
| 6.2 | Marketing Partners Onboarded through (LoA/LoI/MoU) | Non-Key | 10 | 0 | 0% |
| 6.3 | Incubatees linked to online/offline Market | Key Indicator | 150 | 15 | 10% |
| 7 | Business Acceleration Services |  |  |  |  |
| 7.1 | No of Partners outreach | Non-Key | 2 | 0 | 0% |
| 7.2 | Initiation of acceleration and co-incubation services | Key Indicator | 150 | 15 | 10% |
| 8 | Funding & Schematic Convergence |  |  |  |  |
| 8.1 | Schematic Convergence | Key Indicator | 300 | 48 | 16% |
| 8.2 | Support to MUY Incubatee through Reap | Key Indicator | 50 | 4 | 8% |
| 8.3 | Incubatees Pitch Deck Preparation | Key Indicator | 20 | 0 | 0% |
| 8.4 | Demo Days | Key Indicator | 1 | 0 | 0% |
| 8.5 | No of Partners outreach | Non-Key | 5 | 0 | 0% |
| 9 | Other Support Services |  |  |  |  |
| 9.1 | Business Model Canvas | Key Indicator | 600 | 185 | 31% |
| 9.2 | Other Support Services - Labelling, Packaging, Logo Designing etc. | Non-Key | 0 | 2 | — |
| 10 | Branding, Communication & Knowledge Management |  |  |  |  |
| 10.1 | Social Media Post | Key Indicator | 10 | 3 | 30% |
| 10.2 | Preparation of Case Studies and Testimonials | Key Indicator | 10 | 1 | 10% |
| 10.3 | MUY Newsletter | Key Indicator | — | 0 | — |
| 10.4 | IEC & Promotional Activities for MUY | Non-Key | 1 | 0 | 0% |
| 10.5 | Buyer-Seller Meet | Key Indicator | 0 | 0 | — |
| 10.6 | Events/ Seminars/ Workshops | Key Indicator | 0 | 0 | — |
| 11 | Product Development |  |  |  |  |
| 11.1 | Identification and Submission of Proposal for New Product Development | Key Indicator | 0 | 0 | — |
| 12 | Synergies Across Line Departments |  |  |  |  |
| 12.1 | Stakeholder Consultation Workshop | Key Indicator | 0 | 0 | — |
| 12.2 | Meeting of staff with Line Department at Spoke/Hub/State Level | Non-Key | 5 | 1 | 20% |

The above-mentioned progress is based on the IT/MIS system developed under the Mukhyamantri Udyamshala Yojana and the applicable maker-checker approval workflow.

# 3. District-wise Progress

District-wise CFA and onboarding achievements recorded during the selected month.

| S.N. | District | CFA applications | Incubatees onboarded |
| --- | --- | --- | --- |
| 1 | Almora | 42 | 0 |
| 2 | Bageshwar | 2 | 0 |
| 3 | Chamoli | 114 | 0 |
| 4 | Champawat | 61 | 0 |
| 5 | Dehradun | 97 | 0 |
| 6 | Haridwar | 106 | 0 |
| 7 | Nainital | 158 | 0 |
| 8 | Pauri Garhwal | 114 | 0 |
| 9 | Pithoragarh | 101 | 0 |
| 10 | Rudraprayag | 20 | 0 |
| 11 | Tehri Garhwal | 20 | 0 |
| 12 | Udham Singh Nagar | 4 | 0 |
| 13 | Uttarkashi | 70 | 0 |

# 4. Program Workstream Progress

## Outreach and Mobilisation

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 1.1 | Call for Application | 909 |
| 1.2 | District Level Workshops | 3 |
| 1.3 | No. of Awareness cum Outreach activities for SHG members/Potential Lakhpati Didis/ SHGs/CBOs etc. | 24 |
| 1.3.1 | Participants in Awareness cum Outreach activities | 574 |
| 1.4 | EAP/EDP Sessions | 12 |

## Identification and Onboarding of Enterprises

No approved achievement was recorded for this workstream during August 2026.

## Training & Capacity Building

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 3.1 | Business Skills Training Sessions | 7 |
| 3.2 | Incubatees taken Part in Business Modules Training | 212 |
| 3.3.1 | Technical Trainings to Potential Lakhpati Didis/ SHG Members/ CBOs | 1 |

## Business Formalization

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 4.1.1 | Business Registration | 74 |
| 4.2.1 | Artisan Card | 8 |
| 4.2.2 | FSSAI | 14 |
| 4.2.3 | UTDB | 1 |
| 4.2.4 | GST Registration | 4 |
| 4.2.5 | Trademark application filling | 1 |
| 4.2.7 | Advance Licensing Support (Mandi Licensing, Lab Test etc.) | 1 |

## Mentorship

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 5.1 | Specialized Mentorship Support | 25 |

## Partnership & Forward Linkages

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 6.1 | No of Partners outreach | 11 |
| 6.3 | Incubatees linked to online/offline Market | 15 |

## Business Acceleration Services

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 7.2 | Initiation of acceleration and co-incubation services | 15 |

## Funding & Schematic Convergence

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 8.1 | Schematic Convergence | 48 |
| 8.2 | Support to MUY Incubatee through Reap | 4 |

## Other Support Services

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 9.1 | Business Model Canvas | 185 |
| 9.2 | Other Support Services - Labelling, Packaging, Logo Designing etc. | 2 |

## Branding, Communication & Knowledge Management

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 10.1 | Social Media Post | 3 |
| 10.2 | Preparation of Case Studies and Testimonials | 1 |

## Product Development

No approved achievement was recorded for this workstream during August 2026.

## Synergies Across Line Departments

| S.No. | Indicator | Achievement |
| --- | --- | --- |
| 12.2 | Meeting of staff with Line Department at Spoke/Hub/State Level | 1 |

# 5. Field Highlights

Approved field photographs available in the MIS Media Gallery for the reporting month.

| Block Workshops - Dasholi Chamoli ¦ 16 Aug 2026 | Block Workshops - Narayanbagar Chamoli ¦ 13 Aug 2026 |
| --- | --- |
| District Workshops - District workshop Rudraprayag ¦ 05 Aug 2026 | District Workshops - District workshop Pauri Garhwal ¦ 05 Aug 2026 |

| EAP / EDP Sessions - EAP/EDP session Pauri Garhwal ¦ 17 Aug 2026 | EAP / EDP Sessions - EAP/EDP session Tehri Garhwal ¦ 14 Aug 2026 |
| --- | --- |
| Lakhpati Technical Trainings - Importance of Social Media Management in collaboration with Upliftlive Foundation Pauri Garhwal ¦ 07 Aug 2026 | Line Department Meetings - Education — ¦ 17 Aug 2026 |

# 6. Report Basis and Data Notes

- Reporting period: 01 Aug 2026 to 31 Aug 2026.

- Fiscal year: FY 2026-27.

- Achievements are generated from approved MIS records and the existing MUY deliverables reporting logic.

- Cumulative values cover the start of the fiscal year through the end of the selected month.

- Field photographs are selected from Media Gallery records that satisfy the module visibility and approval rules.

- A zero indicates that no qualifying approved record was found under the applicable MIS logic; it does not replace independent program validation.

Report generated on 18 Aug 2026, 12:23 PM.

Thank You - This report is generated from the MUY MIS for the selected reporting month and is intended for programme review. - The document should be reviewed by the State Project Management Unit before external circulation. - The report may contain forward-looking actions and operational observations that remain subject to validation.