MUKHYAMANTRI UDYAMSHALA YOJANA

Monthly Progress Report

Mukhyamantri Udyamshala Yojana

July 2026

Generated from the MUY Management Information System

Private & Confidential

# Table of Contents

| 1. | Progress in Mukhyamantri Udyamshala Yojana (MUY) |
| --- | --- |
| 2. | Quantitative Progress - Plan vs Achievements |
| 3. | District-wise Progress |
| 4. | Program Workstream Progress |
| 5. | Field Highlights |
| 6. | Report Basis and Data Notes |

# 1. Progress in Mukhyamantri Udyamshala Yojana (MUY)

This Monthly Progress Report presents MIS-recorded progress for July 2026. Targets and achievements follow the approved MUY deliverables matrix for FY 2026-27.

| 2,210 CFA applications | 612 Incubatees onboarded | 7 Indicators reporting progress |
| --- | --- | --- |

## Key monthly highlights

- Call for Application: 2,210 achieved against a monthly target of 2,500.

- Incubatees Onboarded: 612 achieved against a monthly target of 700.

- Business Registration: 401 achieved against a monthly target of 325.

- FSSAI: 175 achieved against a monthly target of 130.

- Specialized Mentorship Support: 84 achieved against a monthly target of 65.

- EAP/EDP Sessions: 44 achieved against a monthly target of 39.

- District Level Workshops: 11 achieved against a monthly target of 13.

# 2. Quantitative Progress - Plan vs Achievements

Monthly and fiscal-year cumulative achievements are displayed side by side.

| S.N. | Indicator | Type | Monthly target | Monthly achievement | Monthly % | Cumulative target | Cumulative achievement | Cumulative % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Mobilization and Outreach |  |  |  |  |  |  |  |
| 1.1 | Call for Application | Key Indicator | 2,500 | 2,210 | 88% | 10,000 | 8,420 | 84% |
| 1.2 | District Level Workshops | Key Indicator | 13 | 11 | 85% | 39 | 31 | 79% |
| 1.3 | EAP/EDP Sessions | Key Indicator | 39 | 44 | 113% | 117 | 109 | 93% |
| 2 | Screening & Onboarding |  |  |  |  |  |  |  |
| 2.1 | Incubatees Onboarded | Key Indicator | 700 | 612 | 87% | 2,100 | 1,874 | 89% |
| 4 | Business Formalization |  |  |  |  |  |  |  |
| 4.1 | Business Registration |  |  |  |  |  |  |  |
| 4.1.1 | Business Registration | Key Indicator | 325 | 401 | 123% | 975 | 1,110 | 114% |
| 4.2.2 | FSSAI | Non-Key | 130 | 175 | 135% | 390 | 455 | 117% |
| 5 | Mentorship |  |  |  |  |  |  |  |
| 5.1 | Specialized Mentorship Support | Key Indicator | 65 | 84 | 129% | 195 | 220 | 113% |

# 3. District-wise Progress

District-wise CFA and onboarding achievements recorded during the selected month.

| S.N. | District | CFA applications | Incubatees onboarded |
| --- | --- | --- | --- |
| 1 | Almora | 185 | 49 |
| 2 | Bageshwar | 171 | 42 |
| 3 | Chamoli | 206 | 55 |
| 4 | Champawat | 148 | 38 |
| 5 | Dehradun | 220 | 61 |
| 6 | Haridwar | 194 | 53 |
| 7 | Nainital | 243 | 68 |
| 8 | Pauri Garhwal | 176 | 47 |
| 9 | Pithoragarh | 166 | 44 |
| 10 | Rudraprayag | 139 | 37 |
| 11 | Tehri Garhwal | 181 | 48 |
| 12 | Udham Singh Nagar | 225 | 60 |
| 13 | Uttarkashi | 156 | 40 |

# 4. Program Workstream Progress

## Mobilization and Outreach

- Call for Application: 2,210

- District Level Workshops: 11

- EAP/EDP Sessions: 44

## Screening & Onboarding

- Incubatees Onboarded: 612

## Business Formalization

- Business Registration: 401

- FSSAI: 175

## Mentorship

- Specialized Mentorship Support: 84

# 5. Field Highlights

Approved field photographs available in the MIS Media Gallery for the reporting month.

No approved field photographs were available for this month.

# 6. Report Basis and Data Notes

- Reporting period: 01 Jul 2026 to 31 Jul 2026.

- Fiscal year: FY 2026-27.

- Achievements are generated from approved MIS records and the existing MUY deliverables reporting logic.

- Cumulative values cover the start of the fiscal year through the end of the selected month.

- Field photographs are selected from Media Gallery records that satisfy the module visibility and approval rules.

- A zero indicates that no qualifying approved record was found under the applicable MIS logic; it does not replace independent program validation.

Report generated on 17 Aug 2026, 05:26 PM.